## Process - RFP
Bid Process for RFP and Unsolicited proposals
# | Task Name | Sales Team | Bid support | Tech Sales | PU BD | PU Cust Engg/ Scoping team | Timelines | Comments/Remarks
1. Bid Initiation (should be completed within 24hrs of receiving RFP) | [8 empty] | Legend
1.1 | Receive RFP/proposal request | Ö | [5 empty] | Minimum SLA for RFP response preparation - 10 working days. PU may request for more time based on the complexity of the RFP/requirement. | Ö | Owner
1.2 | SCORE entry made and forward RFP to presales manager | Ö |  |  |  |  | Within 24 hours from Task 1.1 | Entry of opportunity in SCORE is mandaotry
1.3 | Create opportunity brief and circulate to all stake holders |  | Ö |  |  |  |  | Short PPT which describes the high level RFP expectations and the required deliverables & timelines. Stake holders: Sales, Technical Sales, PU BD, PU solutioning
1.4 | Fill Bid Go/No-Go form in SCORE so that the same can be discussed in the meeting | Ö | [5 empty] | Detailed comments need to be provided for all questions
1.5 | Call for bid review meeting |  | Ö |  |  |  |  | Mandatory participants: Sales, Bid support, Tech sales, PU BD/Scoping team. Optional participants: FA, Legal, DPM, HoDs (as required)
1.6 | Circulate MOM of review meeting |  | Ö
2. Team Identification & Plan
2.1 | Identify Bid Response Team |  | Ö |  | Ö |  | Within 24 hours from Task 1.5 (if decision is GO)
2.2 | Bid tool entry and document allocation |  | Ö |  |  |  |  | Create project, create required document placeholders, allocate to various stake holders
2.3 | Prepare a bid plan and publish at defined intervals and track the same to closure |  | Ö |  |  |  |  | Risks identified need to be highlighted and mitigation plan put in place
3. Clarity Call & RFP Questonnaire
3.1 | Prepare query questionnaire |  |  |  | Ö | Ö | Within 24-48 hrs from Task 2.2 or within the specified date whichever is earlier
3.2 | Submit questionnaire to customer |  | Ö
3.3 | Have a clarity call with customer, if needed. | Ö | Ö |  |  |  |  | Sales to facilitate this call. Additional expectations from sales: 1. Information on Competition, budget available. 2. Mapping of decision makers
3.4 | In case of unsolicited proposals, prepare a BRD after the clarity call and get it signed off from customer. |  |  |  | Ö | Ö |  | The intention is to make sure that customer agrees to the requirements and we are on same page. This document is different from the final detailed scope document.
3.5 | Customer Response on Questionarie to be shared with technical Sales/PU BD/PU solutioning |  | Ö
4. Prepare RFP Response (SoC, BoM, proposals, etc)
4.1 | Prepare the Statement of Compliance - funcitonal and technical requirement |  |  |  |  | Ö
4.2 | Prepare Bill of Material |  |  |  |  | Ö |  | Std BoM to be prepared by Technical presales manager and reviewed by PU cust engg team
4.3 | Prepare solution document/technical proposal |  |  |  |  | Ö |  | Final reviewed documents to reach sales atleast 2 working days before the final submission date
4.4 | Prepare the Statement of Compliance for non-funcitonal and non-technical |  | Ö |  |  |  |  | Information like company info, perf bond/BG, etc
4.5 | Prepare gap analysis and identify customization |  |  |  |  | Ö |  | Can be used to costing purpose and for updating the roadmap/release plans
4.6 | Combining and optimizing the BoM and the solution document for Multi PU proposals |  |  | Ö |  |  |  | The optimised BoQ and combined solution to be sent back to the PU teams and their concurrence to be taken. For any queries regarding the combined solution/BoQ post PO, the Technical sales team can be contacted.
4.7 | Send final BoM to SCM for pricing |  | Ö
4.8 | Prepape Business case (in case of rev share model) and get FA approval |  |  |  | Ö
4.9 | Prepare PCS and share |  |  |  | Ö |  |  | PCS is mandatory.
4.1 | Prepape commercial proposal |  | Ö |  |  |  |  | PU BD to review and approve
5. Review Technical & Commercial Proposal
5.1 | Review of commercial proposal | Ö
5.2 | Review of BoM and technical proposal/Solution document (For multi PU and high value solutions) |  |  | Ö
5.3 | Pricing discussions (in case required) | Ö
5.4 | Final Commercial proposal |  | Ö |  |  |  |  | In case of any changes required. To be re-approved by PU BD, before submission to customer.
6. Finalize Proposal & Submission
6.1 | Collate all the required deliverables and submit to Sales |  | Ö |  |  |  |  | All other standard documents, contract/legal documents, etc to be collated.
6.2 | Final review | Ö
6.3 | Print out and Submit Proposal | Ö