## Slide 1
Weekly Project review
Thursday, 10th Dec, 2015

## Slide 2: ATP Readiness
 |  |  |  |  |  |  | Form A |  |  |  | Form B | 
Site | Documentation | TeMIP Integration | MYCOM Integration | B&R Integration | PIM Integration | CLMS Integration | Labelling | L2 & Presentation | ATP-A Offer Date | Pre-ATP | ATP-B Offer date | Pre-ATP
Mumbai | NDD: Shared ODD: Shared NIT: Shared | Handed over to NOC for testing | Handed over to NPO team | HPOO integration testing completed in IOT. Testing is planned on 11th in production. | Integration done for Mumbai Site Data shared for other sites. Integration in progress. Targeted to be closed by 14th Dec | A Meeting is to be planned with CLMS team. |  | 14th Dec | 14th Dec | 11th Dec | 24th Dec | SMSC-25/29 SMSGW-19/23 CRBT-18/22 MCA-18/22 DNC-17/21 TV-18/22
Bangalore | NDD: Shared ODD: Shared NIT: Shared | Handed over to NOC for testing | Handed over to NPO team |  |  |  | F5 Labeling Pending | 10th Dec | 10th Dec | Completed | 16th Dec | SMSC-25/29 CRBT-18/22 MCA-18/22
Kolkata | NDD: Shared ODD: Shared NIT: shared | Handed over to NOC for testing | Handed over to NPO team |  |  |  |  | 11th Dec | 11th Dec | Completed | 18th Dec | SMSC-25/29 CRBT-18/22 MCA-18/22
Hyderabad | NDD: Shared ODD: Shared NIT: Shared | Handed over to NOC for testing | Handed over to NPO team |  |  |  | F5 labels to be pasted by 11-Dec | Offered for ATP | Offered for ATP | Completed | 14th Dec | SMSC-25/29 CRBT-18/22 MCA-18/22
Nagpur | NDD: Shared ODD: Shared NIT: Shared | Handed over to NOC for testing | Handed over to NPO team |  |  |  |  | 12th Dec | 12th Dec | Completed | 20th Dec | SMSC-25/29 CRBT-18/22 MCA-18/22
Lucknow | NDD: Shared ODD: Shared NIT: Shared | Handed over to NOC for testing | Handed over to NPO team |  |  |  |  | 13th Dec | 13th Dec | Completed | 20th Dec | SMSC-25/29 CRBT-18/22 MCA-18/22
Ahmedabad | NDD: Shared ODD: Shared NIT: Shared | Handed over to NOC for testing | Handed over to NPO team |  |  |  |  | 15th Dec | 15th Dec | Completed | 22nd Dec | SMSC-25/29 CRBT-18/22 MCA-18/22
Delhi | NDD: Shared ODD: Shared NIT: Shared | Handed over to NOC for testing | Handed over to NPO team |  |  |  | Target by RJIL SPOC: 14-Dec F5 Labeling pending | 16th Dec | 16th Dec | 15th Dec | 26th Dec | SMSC-25/29 CRBT-18/22 MCA-18/22

## Slide 3: Deployment Status- 14 CRBT Circle
S No | Circle | EMC NAS Availability at the site (Y/N) | EMC NAS installation Status | HP Blade Server Availability at the site (Y/N) | HP Blade Server Installation Status | Power Availability | Rack Availability | Network Readiness | OS Installation Status
1 | Patna |  | N |  | N | 10-Dec |  | 9th Dec | 
2 | Shimla | Location to be shifted to SAG 2 location (15-Dec) |  |  |  |  |  | TOR PORT Mapping not received | 
3 | Kochi |  | N |  | N |  |  | 9th Dec | 
4 | Bhopal |  | N |  | N | 15-Dec |  | TOR PORT Mapping not received | 
5 | Guwahati |  | N |  | N | 17-Dec |  | TOR PORT Mapping not received | 
6 | Shillong | Available at WH | N | Available at WH | N | To be installed at new floor 15-Dec |  | TOR PORT Mapping not received | 
7 | Srinagar |  | N |  | N |  |  |  | awaiting confirmation from RJIL SPOC
8 | Ludhiana |  |  |  |  |  |  |  | 
9 | Ambala |  |  |  |  |  |  | Cabling to be completed by 12-Dec | 
10 | Jaipur |  |  |  |  |  |  |  | 
11 | Agra |  |  |  |  |  |  |  | 
12 | Bhubaneshwar |  |  |  |  |  |  |  | 
13 | Asansol |  |  |  |  |  |  |  | 
14 | Chennai |  |  |  |  |  |  |  | 

## Slide 4: MDB Deployment Status
TASK | Task code | DETAILS | Start date | Closure Date | Status | Comments
Application & Base Package Installation with configurations | CRBT MDB deployment and configuration | MDB binaries installation and configuration | 18-Nov-15 | 19-Nov-15 | Done | 
 | SMSGW deployment and configuration | SMSGW binaries installation and configuration | 20-Nov-15 | 20-Nov-15 | Done | 
 | Omega deployment and configuration | Omega binaries installation and configuration | 21-Nov-15 | 21-Nov-15 | Done | 
 | CRBT FE deployment and configuration | FrontEnd installation and configuration | 23-Nov-15 | 23-Nov-15 | Done | 
 | CMS Installation & Config | CMS Installation & Config | Dependency on NAS for integration |  | In Progress | Content to be received from RJIL
 | IVR deployment and configuration | IVR installation and configuration | Under SIT |  |  | Under SIT. Issue at TAS to be resolved by Nokia
Integration | SMSC integration | integration with client SMSC | 24-Nov-15 | 30-Nov-15 |  | 
 | Tibco integration | integration with Tibco for prepaid & Postpaid billing | 25-Nov-15 | 26-Nov-15 |  | Will be available in Production by 18th Dec for integration
 | SE integration |  | Under SIT |  |  | Will be available in Production by 18th Dec for integration
 | NAS Integration | NAS mounting on Content Sync Server & MRF (22 sites) | In Progress |  |  | Pending on MRF and EMC
 | Content SS installation on 14 circles | Installation/TOR mapping | In Progress |  |  | 
 | IVR integration | Network integration | Under SIT |  |  | Under SIT

## Slide 5: Deployment Status - Messaging
Site | P2P SMSC Readiness | A2P Internal SMSC Readiness | A2P External SMSC Readiness | SMSGW Readiness | STP Integration | LB Integration | MNP Integration | DRA Integration | Cloudmark Integration | OAM Readiness | CDR readiness for Mediation | Proposed Cutover | Remarks
Bangalore |  |  |  |  |  |  |  |  | 17th Dec |  |  |  | 
Kolkata |  |  |  |  |  |  |  |  |  |  | PE to deploy patch is planned on 10-Dec; |  | 
Delhi |  |  |  |  |  |  |  |  |  |  |  |  | 
Nagpur |  |  | NA | NA |  |  |  |  | 17th Dec |  |  |  | 
Hyderabad |  |  | NA | NA |  |  |  |  |  |  |  |  | 
Lucknow |  |  | NA | NA |  |  |  |  | 18th Dec |  |  |  | 
Mumbai |  |  |  |  |  |  |  |  |  |  |  |  | 
Ahmedabad |  |  | NA | NA |  |  |  |  |  |  |  |  | 

## Slide 6: DR Site Progress
Site | Nagpur DR | Hardware Installation | OS Installation | Bonding | YUM Configuration | EMC Configuration | Multipathing | Clustering | DB Installation | Application Installation and Commissioning | Integration | Remarks
Nagpur DR | MLS (48 servers) |  |  |  |  |  |  |  |  |  | 10-Dec | 
 | MBS (23 servers) |  | 20 servers | 20 servers | 20 servers | 20 servers | 20 servers | 20 servers | 20 servers | 16-Dec | 21-Dec | 
Mumbai DR | MLS (25 servers) |  |  |  |  | Network Cabling Pending (10-Dec) | 11-Dec | 12-Dec | 13-Dec | 22-Dec | 31-Dec | F5 to be powered on by 10-Dec
 | MBS (20 servers) |  |  |  |  | Network Cabling Pending (10-Dec) | 11-Dec | 13-Dec | 14-Dec | 24-Dec | 02-Jan | F5 to be powered on by 10-Dec

## Slide 7: Security vulnerability
IOT:
    SMSC: [3/11]
      1 OS related to be fixed by 10th Dec
      1 Application related offered
      1 Open ports related to be fixed by 18th Dec
    SMSGW: [1/11]
      1 Open ports related to be fixed by 18th Dec
    CRBT: [2/10]
      1 OS related to be fixed by 10th Dec
      1 Open ports related to be fixed by 18th Dec
    MCA/DNC/TV: [1/10]
      Open ports related to be fixed by 18th Dec
Production:
    PEs planned after Pre-ATP PEs are over
    8 PEs will be required starting from 18th Dec
    All the security points closed in IOT, till 09th Dec, planned to be fixed in Production by 25th Dec