## Storage UAT
Storage Switch UAT Checklist
S/No. | Test Case | Input Data | Expected Result | Actual Test Results | Required | Status | Artifacts | Remarks
1 | Verify the Storage Hardware Installation. | Verify physically Hardware Installation as per OEM. | Hardware should me rackmounted as per OEM recmondation. |  | YES | YES
2 | Verify SAS & Fiber Cable connection | Verify the cables Physically | SAS & Fiber cable connection should be as per OEM recmondation. |  | YES | YES
3 | Verify the storage licenses & registration | Update the licenses and register with OEM. | License Should be updated |  | NO | NO
4 | Simulate Storage Processor/Controller (SPA/SPB)/Controller failure (CTRL-A/CTRL-B. | • Start continuous I/O on server. • Remove one storage processor • Check that I/O is still running, and that the server can still access all disks. • LUNS will be trespassed to the peer SP. • Check that the SAN Clients still can access the LUN (Only for SAN Configuration) | Check that the SAN Clients still can access the LUN (Only for SAN Configuration) |  | NO | NO
5 | Simulate Storage Processor/Controller (SPA/SPB)/Controller failure(CTRL-A/CTRL-B. | • Re-insert the previously removed SP/Cont. • Check that I/O is still running, and that the serveroller can still access all disks. • LUNS trespassed back to the original SP. | Check that I/O is still running, and that the server can still access all disks. |  | NO | NO
6 | Switch off one power source | • From the PDU, switch off one power source . • Verify the system is running on the single power source. • This test is transparent to host operations. | Storage system should be running on the single power source |  | NO | NO
7 | Switch on the power source back | Verify that the SPS (Standby Power Supply) start charging and become normal. | Storage system should be running on the single power source |  | NO | NO
8 | Simulate “failed” path | • Start continuous I/O on server. • Remove the cable from FC Port of the SP/Controller. • Make sure the I/O is still running on the host without any problem. multipath should show that corresponding path as dead and redirect the I/O’s to other available paths. • These tests are transparent to the hosts. • There may be marginal to noticeable performance impact depending on the number of paths configured to hosts. | Make sure the I/O is still running on the host without any problem. Multipath should show that corresponding path as dead and redirect the I/O’s to other available paths. |  | NO | NO
9 | Re-commission “recovered” path | multipath should automatically enable the re-commissioned path. | Make sure the I/O is still running on the host without any problem. Multipath should show that corresponding path as dead and redirect the I/O’s to other available paths. |  | NO | NO
10 | Simulate Drive failure | Start continuous I/O on the host. • Remove a drive from a RAID Group (RAID 1, 1/0, or 5). • Check that the Hot Spare kicks-in for the failed drive. • Check that the I/O is still running, and that the server can still access all LUNs. | Check that the I/O is still running, and that the server can still access all LUNs. |  | NO | NO
11 | Replace the failed drive | • Check that the Hot Spare transfers back to the now replaced drive. • Check that the I/O process is still running, and that the server can still access all luns. | Check that the I/O is still running, and that the server can still access all LUNs. |  | NO | NO
12 | Storage Management Utility(SMU) | Ensure that the Array can be managed using the SMU running on the Array itself or from the management host. Test CLI Access of Storage. GUI Access on HTTPS | SMU running and manage the Array. Access with CLI. GUI should access with HTTPS. |  | NO | NO
13 | Verify client to SAN connectivity | • Remove one of the Fiber cable from Host Port 1 or Port 2. • Check that there is no disturbance to client connectivity. | Make sure the I/O is still running on the host without any problem. multipath should show that all paths active and optimal. |  | NO | NO
14 | Management Console Testing | • Unplug the Mgmt. port cable from SPA. • SMU application should be accessible from peer SPB. • Plug the cable on SPACtrl A Mgmt. port. • Unplug the Mgmt. port cable from SPB/CtrlB. • Unisphere application should be accessible from peer SPA. • Plug the cable on SPA/CtrlA Mgmt. port | SMU application should be accessible. |  | NO | NO