## Index
Scope of Work document Release Date:: < Date > Ver No:: < X.Y >
Sr No: | Items
1 | EMC installation & Configuration SOW
2 | Generic Hardware installation SOW
3 | Complete Installation SOW
4 | SUN Hardware & OS complete installation SOW
5 | LAN Switch installation and configuration SOW
6 | Firewall installation and configuration SOW
7 | Load Balancer installation and configuration SOW

## EMC
Objective
The document contains the activities to be performed by third party vendor for H/W and S/W installation of EMC The objective of the document is to provide the onsite team complete visibility with respect to the installation activities. The document shall cover installations of applicable devices but the vendor is expected to work beyond the scope mentioned in the document, to achieve success in the project.
S.No. | EMC Scope of Work | Remarks
1 Prerequisites Check Up
1.1 | Verification of Compatibility of Hardware
1.2 | Validation of EMC and server hardware compatibility along with OS version
1.3 | Validation of OS kernel compatibility, Patch set may be required for this specific release of hardware using the Redhat site and vendor release note.
1.4 | Verify EMC BOX as per BOQ/Packing List. | BOQ & Packing list will be provided by PM
1.5 | Collecting of All devices Serial number, Make, Model Details.
2 EMC Installation & Configuration
2.1 | Mounting of storage in the Rack.
2.2 | Powering-On storage. | Power requirement must be verified
2.3 | Updating the Firmware & Software Versions of the Storage.
2.4 | Validation of OS kernel compatibility with EMC version. To register SAN/NAS host agent.
2.5 | Ensure the firmware and BIOS is latest and updated.
2.6 | Verification of Firmware version
2.7 | Ensure the updated firmware of device with authenticated documents released by principle manufacturer(EMC) of hardware.
2.8 | 24 hrs Power ON Hardware burning test
2.9 | Verify WWN Number according to the host.
2.10 | SAN switch zone configuration for EMC and Servers.
2.11 | Configuration of RAID and logical drive. As per partition document provided by MComviva during the installaion. | Partition document will be provided by Solutioing team
2.12 | Host agent binary installtion in server.
2.13 | HOST mapping according to the shared document.
2.14 | Verification & performance testing of Mount Points | testing steps will be provided by solutioing/implementation team
2.15 | Labeling and dressing of EMC storage .
2.16 | Handover of configuration Document to Comviva in Mahindra Comviva format
Index

## Generic Hardware Installation
Objective
The document contains the activities to be performed by third party vendor for H/W and Firmware installation onsite. The objective of the document is to provide the onsite team complete visibility with respect to the installation activities. The document shall cover installations of applicable devices but the vendor is expected to work beyond the scope mentioned in the document, to achieve success in the project.
S.No. | Generic Hardware Installation Scope of Work | Remarks
1 Prerequisites Check Up
1.1 | Verify Hardware component according to the BOQ Document and packing list.. | BOQ & Packing list will be provided by PM
1.2 | Collect all devices Serial Number, Model Number.
1.3 | Need to collect Rack Name and Rack Position Number.
2 Hardware Installation-Chassis ,Servers.
2.1 | Mounting of hardware in Rack such as HP PDU, Chassis, and Server Storage.
2.2 | Powering-On hardware devices. | Power requirement must be verified
2.3 | Blade server / Rack Server Add-on component configuration. Such as – HBA Card/ NIC Card/ RAID Controller.
2.4 | Update latest Firmware and BIOS.
2.5 | Configure ILO / Management IP as per shared IP document.
2.6 | Chassis Onboard Administrator configuration as per shared document.
2.7 | Chassis BNT Switch configuration as per shared document.
2.8 | Chassis VC flex switch configuration as per shared document.
2.9 | Chassis SAN switch configuration / Zoning as per shared document.
2.10 | Power on Self-Test (POST).
2.11 | Proper Cabling of all rack mountable device.
2.12 | Proper Labeling of all rack Mountable device and cable.
2.13 | All device Hardware Configuration backup
2.14 | Handover of configuration Document to Comviva in Mahindra Comviva format
Index

## Complete installation
Objective
The document contains the activities to be performed completely by third party vendor for H/W and S/W installation. The objective of the document is to provide the onsite team complete visibility with respect to the installation activities. The document shall cover installations of applicable devices but the vendor is expected to work beyond the scope mentioned in the document, to achieve success in the project.
S.No. | Complete installation Scope of Work | Remarks
1 Prerequisites Check Up
1.1 | Survey of Implementation Site, as per site survey check list.
1.2 | Physical Verification H/W as per shipment packing list. | BOQ & Packing list will be provided by PM
1.3 | Physical Verification of Bill of Material (BOM)
1.4 | Un-Packaging of Hardware at Installation Site & Assemble server
1.5 | Cross-Checking With Packing List
1.6 | Rack installation and placement
2 Hardware Installation-Servers, Switches, Storage and Tape Drives
2.1 | Mounting of hardware in Rack such as HP PDU, Chassis, and Server Storage.
2.2 | Powering-On hardware devices.
2.3 | Blade server / Rack Server Add-on component configuration. Such as – HBA Card/ NIC Card/ RAID Controller.
2.4 | Update latest Firmware and BIOS.
2.5 | Configure ILO / Management IP as per shared IP document.
2.6 | Chassis Onboard Administrator configuration as per shared document.
2.7 | Chassis BNT Switch configuration as per shared document.
2.8 | Chassis VC flex switch configuration as per shared document.
2.9 | Chassis SAN switch configuration / Zoning as per shared document.
2.10 | Power on Self-Test (POST).
2.11 | Proper Cabling of all rack mountable device.
2.12 | Proper Labeling of all rack Mountable device and cable.
2.13 | All device Hardware Configuration backup
3 Operating System Pre and Post Installation
3.1 | Installation of Operating System (As Per The Comviva Document)
3.2 | Installation of RHEL Packages (As Per Partition Document Provided By COMVIVA)
3.3 | Installation of RHEL OS(Refer the Solution document for OS version)
3.4 | Configuration of IP Address in hardware (As Per Document Provided By COMVIVA)
4 Configuration - Infrastructure, Application
4.1 | YUM Configuration
4.2 | Network Configuration on Servers
4.3 | NTP configuration
4.4 | syslog-ng installation (Based on the Project)
4.5 | Antivirus Installation In Linux Server (Based on the Project)
4.6 | Java installation (Based on the Project)
4.7 | Physical connectivity of Servers, Storage with Network switches
4.8 | Creation of LUNs in Storage, Mapping and mounting of LUNs in
4.9 | Multipathing
4.10 | Configuration of RHEL Cluster in servers.(As Per COMVIVA application team requirement)
4.11 | Server OS hardening.
4.12 | Switch configuration
4.13 | Firewall configuration
4.14 | Cabling
4.15 | labeling
5 Final Testing - Infrastructure, Application & Documentation
5.1 | Checking and verifying Server, Storage
5.2 | Checking and verifying Network Switches and Connectivity
5.3 | OS Hardening & Tuning
5.4 | Testing of Complete Infrastructure (Cluster, network and power of servers and rest hardware )
5.5 | Labeling of Components, Cable tying and dressing
5.6 | Snapshot of Installed Hardware After Integration & Labeling
5.7 | Final testing of all hardware and software
5.8 | Handover of configuration Document to Comviva in Mahindra Comviva format
Index

## SUN Product SOW
Objective
The document contains the activities to be performed completely by third party vendor for SUN H/W and S/W installation. The objective of the document is to provide the onsite team complete visibility with respect to the installation activities. The document shall cover installations of applicable devices but the vendor is expected to work beyond the scope mentioned in the document, to achieve success in the project.
S.No. | SUN installation Scope of Work | Remarks
1 Prerequisites Check Up
1.1 | Survey of Implementation Site, as per site survey check list.
1.2 | Physical Verification H/W as per shipment packing list. | BOQ & Packing list will be provided by PM
1.3 | Physical Verification of Bill of Material (BOM)
1.4 | Un-Packaging of Hardware at Installation Site & Assemble server
1.5 | Cross-Checking With Packing List
1.6 | Rack installation and placement
2 Hardware Installation-Servers, Switches, Storage and Tape Drives
2.1 | Integration of add-on Components (HBA cards, CPU, RAM, Hard Disks etc.)
2.2 | Mounting of all The Hardware in the Rack
2.3 | Powering on The Servers and Initial Testing
2.4 | Updating The Firmware & BIOS Versions of The Servers
2.5 | Configuration of RAID & Logical Drive (As Per Partition Document Provided By COMVIVA)
2.6 | Powering on the Servers, storage & Testing of All Hardware after Integration | Power requirement must be verified
3 Operating System Pre and Post Installation
3.1 | SUN Solaris 11.X in server.
3.2 | Latest Kernel and Errata updates
3.3 | LAN Interface redundancy (IPMP Active-backup) configuration.
3.4 | Hostname & IP configuration.
3.5 | PKG configuration in all servers.
3.6 | Distribution of LDOM on Physical Servers as per the LDOM architecture
3.7 | Configuration of Kernel tuning parameters
4 Configuration - Infrastructure, Application
4.1 | Network Configuration on Servers
4.2 | NTP configuration
4.3 | syslog-ng installation (Based on the Project)
4.4 | Java installation
4.5 | Physical connectivity of Servers, Storage with Network switches
4.6 | Creation of LUNs in Storage, Mapping and mounting of LUNs in
4.7 | SUN Native Multipath configuration and Storage LUN mounting.
4.8 | Configuration of RHEL Cluster in servers.(As Per COMVIVA application team requirement)
4.9 | Configuration of Routes and establish connectivity with integration points.
4.10 | Server OS hardening.
5 Final Testing - Infrastructure, Application & Documentation
5.1 | Checking and verifying Server , Storage
5.2 | Checking and verifying SAN Switches, Storage - Server Connectivity
5.3 | OS Hardening & Tuning
5.4 | Testing of Complete Infrastructure (Cluster, network and power of servers and rest hardware )
5.5 | Labeling of Components, Cable tying and dressing
5.6 | Snapshot of Installed Hardware After Integration & Labeling
5.7 | Final testing of all hardware and software
5.8 | Handover of configuration Document to Comviva in Mahindra Comviva format
Index

## LAN Switch SOW
Objective
The document contains the activities to be performed completely by third party vendor for LAN Switch installation and configuration. The objective of the document is to provide the onsite team complete visibility with respect to the installation activities. The document shall cover installations of applicable devices but the vendor is expected to work beyond the scope mentioned in the document, to achieve success in the project.
S.No. | LAN Switch Scope of Work | Remarks
1 | Hardware delivery verification
2 | Rack space in datacentre for installation of RACKS
3 | Power installation till rack provided by Client
4 | Hardware installation in Rack as per Rack layout
5 | VLAN Creation
6 | Access List Creation
7 | Layer 3 redundancy configuration
8 | SSH Configuration
9 | Spanning tree configuration
10 | Default Gateway Configuration
11 | Routed Port configuration (Connection Termination to Firewall)
12 | Security on ports
13 | Port description configuration
14 | Configuration backup
15 | NTP configured
16 | NTP through management IP
17 | Local time zone
18 | Secured protocols for management
19 | Secured protocols for file transfer
20 | SSH authentication by RSA key
21 | Dedicated management interface
22 | Secured console port
23 | Other interface not accept management traffic
24 | Banner configured
25 | Banner before login
26 | Banner on all administrative access type
27 | Network cabling in intra Rack
28 | uplink cable provided by customer from customer network to platform Rack
29 | Proper dressing of network and power in rack
30 | Labeling of devices in Rack
31 | Labeling of Network cable as per requirement
32 | Handover configuration document to Comviva.
Index

## Firewall SOW
Objective
The document contains the activities to be performed completely by third party vendor for Firewall installation and configuration. The objective of the document is to provide the onsite team complete visibility with respect to the installation activities. The document shall cover installations of applicable devices but the vendor is expected to work beyond the scope mentioned in the document, to achieve success in the project.
S.No. | Firewall installation Scope of Work | Remarks
1 Detailed Activity
1.1 | Hardware delivery verification
1.2 | Rack space in datacentre for installation of RACKS
1.3 | Power installation till rack provided by Client
1.4 | Hardware installation in Rack as per Rack layout
1.5 | Configuration of FW interfaces with IP addresses
1.6 | Configuration on Network Objects
1.7 | Configuration on Group Objects
1.8 | Policy Configuration
1.9 | Nat Configuration
1.10 | DMZ configuration
1.11 | Routing configuration
1.12 | SSH Configuration
1.13 | HA Configuration
1.14 | Configuration document must be handed over to comviva.
2 Firewall checklist – SELF DEFENCE:
2.1 | On the public firewall external facing interface, DoS policies must be configured and activated to detect (status ‘enable’, logging ‘enable’ and action ‘pass’) denial of service attempts against the application.
2.2 | If “access is denied” packets must be dropped silently; no ICMP messages must be returned to the attacker (the firewall must not create or relay any ICMP messages).
2.3 | The final rule must drop and log all traffic.
2.4 | Static routing must be used; intervlan routing must be disabled except for FWO snmp ILO, storage devices and back office user access.
2.5 | “Advanced Routing” feature must be disabled.
3 FIREWALL POLICIES
3.1 | By default all traffic must be blocked, (apart from firewall administration traffic).
3.2 | Firewall object definitions (e.g. IP Addresses) must be precise. For example, network objects must be defined using IP addresses (or the smallest possible subnet mask). DNS domain names must not be used.
3.3 | Source and destination definitions must be the minimal necessary.
3.4 | In the group otherwise more specific groups and rules must be created.
3.5 | Wildcards must not be used in the source or destination of “allow” rules.
3.6 | Wildcards or large port ranges must not be used in “allow” rules.
3.7 | System configuration options must be carefully examined to ensure all security features are enabled including those dealing with logging.
3.8 | Measures to detect Denial of Service attacks must be enabled and only in the public firewall.
4 FIREWALL POLICIES – ANTI-SPOOFING
4.1 | Object definitions must be associated with a specific interface.
4.2 | Zones must be created on all firewalls. Interfaces as well as source and destination zones must appear in policy.
4.3 | Source and destination interfaces must appear in policy
5 FIREWALL POLICIES – FORMATTING
5.1 | Explanatory Comments must be used (Comments)
5.2 | Policies must be grouped in to sections: production (for production flows), administration (for administration flows) and monitoring (for monitoring flows).
5.3 | Naming convention should be used for object names (Cf Naming convention).
6 FIREWALL POLICIES – LOGGING OPTIONS
6.1 | The firewall must log all traffic (except monitoring flows).
6.2 | Logging options must be set at a sufficient level to capture session information.
6.3 | Timestamps on all logs should be synchronised to enable time-based correlation.
6.4 | All firewalls must be configured to synchronize their time with the private F5 load balancer
7 FIREWALL POLICIES – OPERATING SYSTEM SECURITY
7.1 | The version must be FortiOS v5.0 Patch5.
7.2 | Only services mentioned in this document must be installed or enabled on the firewall, all other services must be disabled.
7.3 | Firewalls must be dedicated solely to the firewall function.
8 FIREWALL POLICIES – FW public Vdom requirements
8.1 | Vdoms FWI (Production Firewall) and FWO (Management Firewall) must exist in addition to the default vdom root.
8.2 | Operation mode is NAT for all vdoms.
8.3 | FWO is the only management VDOM.
8.4 | VDOM global resources are set to Default.
9 FIREWALL POLICIES – CONFIG REQUIERMENTS
9.1 | High Availability Mode should be set to Master / Slave.
9.2 | FGCP (FortiGate Cluster Protocol) used a password to protect the cluster membership. This password must follow the same policy as user password.
9.3 | Block intra-zone traffic.
9.4 | The 2 cables between the 2 Firewalls must be used as Heartbeat links.
9.5 | Only flows mentioned in the Flow matrix must exist.
9.6 | More specific rules must be placed before (Primary).
9.7 | Plicy that will be much often must be placed before.(this requirement is secondary)
9.8 | Only NAT mentioned in the Flow matrix must exist.
9.9 | Local time zone must be used.
9.10 | Syslog must be configured on the firewalls and minimum log level set to Information.
9.11 | “Enable Session Pick-up” must be checked.
9.12 | Only 1 cluster group must exist on the fortigate. This cluster group members must be: FWI VDOM, FWO VDOM, root VDOM.
Index

## Load Balancer SOW
Objective
The document contains the activities to be performed completely by third party vendor for Load Balancer installation and configuration. The objective of the document is to provide the onsite team complete visibility with respect to the installation activities. The document shall cover installations of applicable devices but the vendor is expected to work beyond the scope mentioned in the document, to achieve success in the project.
S.No. | Load Balancer Scope of Work | Remarks
1 | Hardware delivery verification
2 | Rack space in datacentre for installation of RACKS
3 | Power installation till rack provided by Client
4 | Hardware installation in Rack as per Rack layout
5 | Configuration of LB interfaces with self IP
6 | VLAN creation
7 | SSH Configuration
8 | Routing Configuration
9 | VS, Node and Pool configuration
10 | SNAT Configuration
11 | Configuration of Health monitoring
12 | HA Configuration
13 | Profile configuration
14 | Priortizing Traffic types through layer 7 policies / persistency
15 | TMOS version+D27:D69
16 | TMOS configuration
17 | TMOS installed on empty volume
18 | Default boot partition
19 | Accounts for different entities
20 | Built-in partition
21 | NTP on administrative interface
22 | Local time zone
23 | Default resource provisioning
24 | Names in uppercase
25 | Redundancy mode
26 | Device number
27 | Redundancy state preference
28 | ConfigSync implementation
29 | Config Sync ip address
30 | Serial and network failover
31 | Secured protocols for management
32 | Secured protocols for file transfer
33 | SSH authentication performed with RSA key
34 | Dedicated management interface
35 | Banner exists
36 | Banner before login
37 | Banner on all administrative access type
38 | No confidential information in the banner
39 | Unused interfaces disabled
40 | Interface mirroring disabled
41 | Default spanning-tree configuration
42 | Interface description
43 | Packet filter disabled
44 | Rate shaping not configured
45 | VLAN tagging only on interfaces that carry several VLANs
46 | Interface does not allow all VLANs
47 | ARP default configuration
48 | Port lockdown only for required traffic
49 | IPv4 used
50 | Web GUI access ciphered
51 | X.509 standard
52 | 048 bits RSA key size
53 | erisign as trusted third party CA
54 | ame public SSL certificate on both sites
55 | No wildcard SSL certificate
56 | No health monitors on nodes
57 | Names for nodes
58 | Ratio and connection limit set with default values
59 | Health monitors for pools
60 | At least OSI layer 4 monitors
61 | Virtual servers listen only on production VLAN
62 | Virtual servers listen only on 1 TCP port
63 | No forwarding, stateless or reject virtual server
64 | Default pool set
65 | SNAT set
66 | Configuration document must be handed over to comviva.
Index